## Instructions
Project Effort Tracker - How to use this workbook
This workbook has 5 tabs:
1. Resources - Master list of all developers and QA (onshore + offshore). Fill this in first (up to 50 rows ready, add more if needed).
2. Jira Tickets - Master list of all ~50 Jira tickets / scope items. Fill this in second.
3. Effort Log - The DAILY ENTRY sheet. Each resource adds one row per ticket per day they worked on it. Location and Role auto-fill from the Resources list once you pick a Resource Name. Multiple people can log the same ticket on the same day (that's expected).
4. Daily Tracker Matrix - Auto-calculated. Shows total hours logged per resource per day (July 3 - Aug 4). Cells highlighted RED mean that resource logged ZERO hours that day, so you can chase missing entries every morning.
5. Ticket Summary - Auto-calculated. Total effort per Jira ticket across all resources and dates.
Only edit cells shaded YELLOW. Everything else is a formula and will break if overwritten.
To add a resource or ticket: insert a new row in the Resources / Jira Tickets sheet within the existing table range so the dropdowns in Effort Log keep working (or extend the named ranges if you add beyond row 51).

## Resources
Resource Name | Location (Onshore/Offshore) | Role (Dev/QA)
Amit Sharma | Offshore | Dev
Priya Nair | Offshore | QA
John Miller | Onshore | Dev
Sara Lopez | Onshore | QA

## Jira Tickets
Jira Ticket | Scope Item / Task Description
PROJ-101 | Build room mapping ingestion service
PROJ-102 | QA regression for booking flow
PROJ-103 | API contract review

## Effort Log
Date | Resource Name | Location | Role | Jira Ticket | Effort (Hours) | Comments
2026-07-03 | Amit Sharma | Offshore | Dev | PROJ-101 | 6 | Initial setup
2026-07-03 | Priya Nair | Offshore | QA | PROJ-102 | 4 | Test case prep
2026-07-03 | John Miller | Onshore | Dev | PROJ-101 | 3 | Code review support

## Daily Tracker Matrix
Resource Name | Location | Role | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04
Amit Sharma | Offshore | Dev | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Priya Nair | Offshore | QA | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
John Miller | Onshore | Dev | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sara Lopez | Onshore | QA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
Legend: Green = hours logged that day. Red = resource exists in master list but logged 0 hours that day (chase this up). Blank = row not yet used for a resource.

## Ticket Summary
Jira Ticket | Scope Item / Task Description | Total Effort (Hours) | # Resources Who Logged Time
PROJ-101 | Build room mapping ingestion service | 9 | 2
PROJ-102 | QA regression for booking flow | 4 | 1
PROJ-103 | API contract review | 0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0